BR007

Performance indicators and means of verification

| Activity | Indicators | Means of verification | Progress and results of activities | Status indicators | File Reference |
| --- | --- | --- | --- | --- | --- |
| 1.Preparatory meeting in Manaus (Amazonas State) with Brazilian organizations with a track-record of working with indigenous groups | - Process followed for organizing and during the meeting - Participants in the meeting - Discussions relevant to indigenous people among SSF | - Progress report - Report on preparatory meeting in Manaus | - Detailed report ready and delivery - Result: Initial planning of the Seminar ready, such as date, lodging, meals, guest list and Seminar programming | - Achieved | BR001 |
| Organization of the Workshop | - Agenda and participants including group photograph - Participation of relevant stakeholdrs including human rights Commission - Process followed and out put of the workshop | - Progress report - Detailed Workshop report - Representatives of local, provincial and federal government | - Workshop took place on March 27 and 28 - Broad participation of indigenous people, representing 17 ethnic groups, and local and federal government entities - Results: Indigenous people from 17 ethnic groups from the state of Amazonas, NGOs and governmental entities from the state of Amazonas became aware of the Guidelines; partici- pants exchanged experiences and contacts to initiate community-based tourism and fisheries management projects in their respective Indigenous Lands; family aquaculture project established between interested indigenous people, university and FUNAI | - Achieved | BR002 |
| Preparation of a synthesis document to be discussed during the Workshop on main issues of concern and policy measures of interest to indigenous groups based on SSF Guidelines | - Experience of the person doing the synthesis paper - ToR for the synthesis paper - Contents for the synthesis paper | Progress report indicating - CV of the person and the ToR for preparation of the synthesis paper - Synthesis document of main issues of fisheries and indigenous people - Proposed agenda and participants for the workshop | - CV, ToR, Synthesis paper, Proposed agenda and participants for the workshop ready e delivery - Result: closure of the Seminar schedule. Written part of the workshop preparatory material is ready - Next step: Definition and purchase of tickets. Art and layout of folders | - Achieved | BR003 |
| Production of audio/visual material covering the workshop proceedings | - Coverage of the audio visual material | - Progress report - Video document (link to the video is in the video document word file) | - Material audio\visual ready and delivery - Result: Video subtitled in English covering the event and containing interviews of participants | - Achieved | BR004 |
| Final report of proceedings and a synthesis document to update the Vital Fisheries strategy | - Agenda and participants including group photograph - Process followed and out put of the workshop - Points and processes in synthesis with regard to a vital fishery strategy in favour of the indigenous groups among SSF | - Progress report - Country Report | - Detailed report ready and delivery - Result: Final report containing all working group discussions and information on the main basins of the State of Amazonas, as well as the ethnic groups living in each basin \ river, land demarcations, protected areas, conflicts and fisheries-related problems of the indigenous peoples of the region | - Achieved | BR005 |