FDA’S CO-MANAGEMENT PLAN														MYR 002

| Sr | Key Activity | Details of Activities | Role of Project | Short-term Objectives | Probable Issues/ Challenges | Capacity Need |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Research and Data Collection | - Collect the fishery related information per village by covering main livelihood (part time or full time), fishing areas, fishing grounds, fishing seasons, etc. - Mapping the existing and proposed fishing groups - Develop understanding on the spawning and larval stages of fish in targeted areas through Participatory Mapping - Identify and map migration, spawning and nursery grounds of key commercially important fish species. - Setting the village-based data-collection system and present the collected information to Development and Government Agencies as needed. | - Conduct surveys and samplings of fishery resources to determine population, species composition and distribution. - Document the current fishing practices in targeted areas - Collect local fisheries knowledge on catch, gear & ecology; - Collect regular data on fish catches from fish buyers; - Determine major fisheries management issues; - Collect socio-economic data on the fishery. | - Systematic publication and documentation of knowledge products of fishery communities | - Poor participation of communities - Weak coordination mechanism among fishery communities | - Indigenous Fishery Training |
| 2 | Identification of Fishing Season and Fishing gears | - Understanding the fish ecology and share the knowledge among the fishing communities based on the results of previous studies - Review SSF’s seasonal usage of different fishing gears to understand the impacts on natural resources - Deliver knowledge to fishery communities about the fishing season, legal fishing gears and norms which are mentioned in the new AFWFL - Carry out awareness raising activity for fishery communities to be able to understand on illegal fishing gears and fishing seasons - Identify the fishing season and fishing gears for co-management area through the community mass meeting and report to DoF for approval - Identify Rules and Regulation for the fishing communities to follow in fishing - Organize the patrolling group and carry out the regular monitoring at targeted zone/ co-management areas | - Develop fishery co- management plans for the targeted area to combat IUU fishing and covering the conservation system, promote sustainable harvest (of fish and other aquatic species), and stock recovery. - Explore to official, government- recognized, co-management zones to negotiate fishery co-management plans - Support co-management committees to develop effective management system in co-management area such as patrolling and conservation practices. | - Protect fish and other aquatic species through the designation of protected area(s). | - Difficult to get approval and permission from GAD and relevant departments to do regular patrolling - High cost involved in regular patrolling | - Fishers’ awareness of legal and illegal fishing |
| 3 | Awareness and Campaigns | - Develop the awareness packages covering aspects of fish ecology, management systems and proper Value Chain practices - Develop the awareness plan in collaboration with VDC, DoF, Village Administrators and Development Agencies - Carry out the awareness and campaign at targeted areas - Work and coordinate with DoF for regular awareness program and IEC development - Deliver the knowledge to children through dissemination of pamphlets and posters at schools - Install the awareness vinyls and posters in targeted areas | - Develop communication strategies and support the implementation of innovative communication tools. - Carry out awareness activites alongside of project area - Support intensive training on ecosystem values and conservation at different levels - Promote awareness rising for sustainable harvest of fishery products through awareness programs. | - Enhance knowledge and awareness of the ecosystem values of the targeted area, species conservation status and its management. | - Difficulties in getting permissions from related departments - Difficult to access financial and technical capital | - Fish ecosystem value training - Fish Preservation and VC training |
| 4 | Zoning and Mapping for Conservation | - Organize community mass meetings to undertake mapping of the proposed conservation zone based on the key findings of fishing grounds mapping - Get agreement among the communities for conservation zone, covering fish spawning grounds, juvenile habitats and other sensitive areas. - Develop the conservation map by using PRA and GIS with the support of project/ development agencies - Develop the management plan through the community mass meeting and share with government agencies for getting approval and acceptance. - Organize the patrolling group and carry out the regular monitoring in the targeted zone | - Undertake studies and surveys on spawning and fish larvae in targeted areas - Identify and map migration, spawning and nursery grounds of key commercially important fish species. - Support to communities on developing maps of fishing zone by GIS in collaboration with government agencies - Develop target habitat management/conservation plan through the designation of protected area and zoning scheme e.g. core zone for spawning and nursery grounds for key fish species. | - Develop and implement fishery co-management arrangements in priority sites to ensure sustainable harvest and stock recovery. | - Difficult to get approvals from related department for conservation and mangrove plantation - Weak capacity of committee members to undertake reporting and communication - Poor participation of the diverse range of stakeholders at different levels | - Co-management and NRM Training |
| 5 | Fishermen/ member selection | - Coordinate and work with DoF, FDAs and VDC and set the criteria for fishing at proposed fishing grounds/ co-management area through meetings with fishery communities - Carry out beneficiary selection based on the criteria - Collect the selected fishermen list and report to DoF for membership registration - Make sure the understanding of selected fishermen on the R&R of co-management area through trainings and awareness | - Strengthening the capacity of FDAs and management committees for organizational management and development - Create the concrete linkages/ networks between fishery communities and government agencies for in-time supports for fishery communities | - Membership registration and improving of access to fishing | - Nil | - Leadership and Organizational Management Training |
| 6 | Mangrove Forest Rehabilitation and Plantation | - Mapping the potential Mangrove plantation area by coordinating with FDA and VDCs - Organize the Mangrove Plantation working group with the participations of a range of stakeholders - Share the mapping results to DoF, FD, LRD, GAD and development agencies - Extend the services of the technician from FD and development agencies to provide the technical support to the communities. - Organize mass meetings with farmers, land owners, government departments and development agencies for land allocation for mangrove plantation - Work with FD for getting the mangrove species, plants and certificate for community forestry - Work with development agencies for funds and support for mangrove plantation - Facilitate the communities to involve in mangrove plantation - Mangrove planting undertaken in the targeted areas with the direct support of the FD and project - Regular monitoring and maintenance by the working group | - Undertake studies to determine existing mangrove distribution and species component in Ayeyarwaddy Region especially for targeted area - Investigate potential for mangrove plantation along the creeks, taking into consideration suitable areas, species to plant, methods used, monitoring and evaluation, and impacts to key fish species - Work with FD and mangroves experts for provision the technical supports to fishery communities - Fund Raising for Mangrove Plantation | - Protect and monitor existing mangrove habitats and, restore, where practicable. | - Difficult to get land for mangrove plantation - Lack of financial capital - Difficult to communicate even within the committees and members | - Fishery Ecology and Mangrove Habitats Training |
| 7 | Law Enforcement, Monitoring and Patrolling | - Organize the monitoring and patrolling team with the members of management committees, representatives of village authority and government departments - Develop the patrolling plan and support needs in collaboration with multi-stakeholders - Develop the R&R for the patrolling team in coordination with DoF and local authority - Carry out regular monitoring and patrolling - Systematic documentation on findings and reporting in-time to relevant agencies/ stakeholders | - Review and revise regulations and enforcement in relation to fish species conservation. - Review and revise regulations in relation to fisheries to tackle IUU and destructive fishing activities and gears, and enhance enforcement - Strengthen the capacity of surveillance and patrol for fish through training course and support to equipment and infrastructure to patrolling team (smart patrolling, GIS, Lens and etc.) - Provide support to awareness raising programs | - Ensure the protection of key species through the enhancement of enforcement mechanisms and the support to awareness programs. | - Difficult to get the recognition from GAD and relevant departments to the patrolling groups - High and recurring patrolling costs | - Bio-diversity Monitoring Training - Smart Patrolling Training |
| 8 | Arrest and actions | - Disseminate the arresting and action program’s objectives/ messages to fishery communities - Create local network for better communication system among fishery communities to monitor illegal fishing in a timely manner. - Systematic recording on illegal fishing by photo or video taking using phone or camera and share in time to concerned authority or government agencies - Support to local authority or DoF to be able to take action on illegal fishermen in line with existing fishery law | - Review the arresting and action mechanisms in the 4/2018 Ayeyarwaddy Fresh Water Fishery Law and By-law - Facilitate and encourage the FDAs and management committees to follow the new laws on developing the management and law-enforcement plan - Create the communication channels between fishery communities and government agencies for timely reporting on illegal fishing | - Communities’ practices improvement in following the legal fishing | - Nil | - Law Awareness Raising |
| 9 | Penalties | - Coordinate with local authority and DoF on developing the penalties for illegal fishing - Identify the penalties based on the type of illegal fishing practices according to the existing fisher law - Share the different types of penalties per illegal fishing practices to the fishery communities and multi-stakeholders | - Support to FDAs and management committees to work in collaboration with DoF and local authorities through a series of meetings to ensure that the penalties in the management plan are in line with existing fishery law. | - Reduce the illegal fishing practices and protect the fishery resources | - Nil | - Law Awareness Raising |
| 10 | Documentation and Reporting | - Documenting the program implementation and process including conservation, patrolling, awareness raising, etc. - Regular progress reporting to FDAs, local authority, DoF, FD and project team - Disseminate progress reports to the development agencies in approved reporting format and measurement framework for systematic documentation and update. - Regular recording and documentation of the meetings, workshops and activity implementation processes (including the decisions of meetings, workshops, etc.) - Creating the better filing system to protect important documents (instructions, guidelines, recommendations, suggestions from local authority and multi-agencies) for validation and future reference. - Organize the committee meetings for regular updating of documented information | - Strengthen the capacity of FDAs and management committee for regular reporting and documentation - Regular collecting the progress reports from FDAs and management committees and share the key findings/ achievements to Policy makers of different levels - Support reporting template and measurement framework for systematic recording and reporting | - Improve documentation alongside of plan implementation and reporting | - Poor knowledge for report writing and meeting minute note taking | - Documenting and Reporting Training |
| 11 | Governance Structures & System | - Organize fishery co-management committees at village and village tract levels in line with new fishery law - Identify the structures, ToR and R&R of management committees in collaboration with fishery communities, VDCs and FDAs - Share the committee information including structures and ToR to DoF and FDAs for recognition - Organize regular coordination meetings involving the committee members with the support of FDAs - Support FDAs to advocate for better fishery management system by sharing the field-level issues faced by the fishers. - Establishment of reporting system and regular reporting to FDAs | - Organize management committees at different levels and identify Rules and Regulations - Ensure regular meetings to analyze existing composition of the committees, identify constraints to the management of resources in the targeted area, and monitoring and evaluation of the management plan. - Encourage and support the community and interest groups in decision-making in resource management and involvement in environmental research and monitoring. - Install the series of documentation system | - Establish and implement transboundary multi-stakeholder - Management Committee and other related local or region/state-level governance bodies to ensure the continual and effective implementation and monitoring of the management plan. | - Poor financial capital for regular coordination meeting | - Good Governance Training - Group/ Association Forming Training |
| 12 | Fishing Right Allocation and License for fishermen | - Work with FDAs and DoF to obtain permission for fishing by assessing the gears and fishing boats being used locally. - Enable fishing licences for fishermen who fish in line with the accepted criteria to operate in the co-management area - Support to approved fishermen for registration at DoF and township FDA - Conduct awareness for fish collectors not to buy the under size (juvenile) fish and crabs and support for collecting licence through management committee - Carry out regular monitoring of fishermen to ensure legal fishing with approved gears | - Support to FDAs and management committees for coordination and negotiation with DoF in giving the permission for fishermen to fish at co-management area based on the criteria | - Enhance communities’ fishing right for livelihood survival | - Poor participation of government agencies in coordination with fish collectors not to collect under-size fish | - Advocacy Training |
| 13 | Fishery Revenue Collection | - Deliver awareness programmes on fishery revenue collection to the communities - Ascertain the fishermen’s views on the issues in existing fishery revenue system - Discuss with fishery communities for better payment system and date - Collect the revenue from fishermen with systematic recording and reporting to FDAs - Pay the collected revenue to DoF on time with recorded documents - Save the original revenue receipt invoices of DoF at FDAs and share copy to fishery communities | - Review on the existing fishery revenue collection practices - Organize fishery revenue awareness training, campaign and provide formats - Coordinate with government agencies and identify the ToR and R&R of fishery association for Revenue Collection | - Enhance community led fishery revenue collection system | - SSF can’t provide the tax in timely | - Fishery Revenue Awareness |
| 14 | Coordination and Information Sharing | - Organize regular coordination meetings at village and village tract levels - Systematic documenting on meetings and workshops’ results and submit to FDAs of different levels - Information on progress with the programme, including financial update to be shared through regular meetings - Encourage the fishery communities and members of FDAs to enhance their participation at meetings and workshops - Prepare and arrange for the participation of local authority and governmental agencies at meetings/ workshops - Set the ToR and R&R for regular coordination meetings and actions/penalties for absentees without prior intimation. - Discuss with FDAs about agenda setting and share advance to proposed participants to get more participation and ideas | - Encourage and support the communities for regular coordination and reporting to Governmental Departments and facilitate the involvement of Government Agencies at communities meetings - Strengthening the FDA and management committees for effective collaboration and coordination with different level stakeholders for sustainable natural resource perspectives - Organize excursion or short trips for the FDAs and Management Committees to selected sites that demonstrate effective Fishery Resource management. - Present the management plan of targeted areas at different levels when possible | - Regular coordination mechanism with Multi-stakeholders and knowledge sharing platform | - Nil | - Coordination and Facilitation Training |
| 15 | Fund Raising | - Open bank account with 3 committee members in line with new fishery law - Collect the membership fees from fishermen - Save money obtained through penalties on illegal fishermen - Work and coordinate with development agencies for potential fundraising opportunities - Link with FDAs and NGOs for alternative livelihood/ income generation opportunities - Regular updating the financial expenditure at the village meetings | - Mapping the proper fund opportunities for FDAs and communities led resource conservation program - Strengthen FDA for financial management and business plan development - Support alternative livelihood opportunities for fishery communities - Create linkages with MFI for better financial opportunities | - Improve financial resources for sustainable fishery and alternative livelihood opportunities | - Nil | - Financial Management Training - SME and business planning training (Alternative livelihood options) - Introduce SSA models and promote for sustainable aquaculture model to enhance science-based management - Improve fishery value chain and support post-harvest training e.g. fish paste, dried fish marketing |